## Cover Page
OPENCART E-COMMERCE PLATFORM BUG TRACKING REPORT V1.0
PROJECT INFORMATION
Project : OpenCart E-Commerce Platform
Client : Portfolio Project
Document Type : Bug Tracking Report
Version : 1.0
Created By : Amisha Modi
Designation : Software Test Engineer
Experience : 4 Years
Testing Period : 02-Feb-2026 to 10-Feb-2026
Total Bugs Found : 14
Critical : 2
High : 5
Medium : 6
Low : 0
BUG STATUS SUMMARY
Status Count
Open 8
In Progress 3
Fixed 2
Closed 1
Deferred 0
MODULE-WISE BUG DISTRIBUTION
Module Bugs
User Account 4
Product & Catalog 4
Cart 3
Checkout 0
Order 0
Payment 0
Tax & Shipping 0
Inventory 0
Admin 0
Admin Role 0
Reports 0
Notifications 0
Promotions 0
Security 3
DOCUMENT CONTROL
Version │ Date │ Author │ Description
────────┼────────────┼──────────────┼────────────────────────
1.0 │ 10-Feb-2026│ Amisha Modi │ Initial bug report
CONFIDENTIAL - Portfolio Project
© 2026 Amisha Modi. All Rights Reserved.

## All Bugs (Master List)
Bug ID | TC ID | Module | Summary | Description | Severity | Priority | Status | Reported Date | Reported By | Assigned To | Environment | Steps to Reproduce | Actual Result | Expected Result | Attachment
BUG-001 | TC_UAM_003 | User Account | Registration accepts invalid email format | User can register with email that doesn't follow standard email format (missing @ and domain) | Medium | P3 | Open | 2026-03-01 | Amisha Modi | Dev Team | Chrome v122 | 1. Go to Registration page 2. Enter "invalid-email" in email field 3. Enter valid password "Test@123" 4. Click Register | Form submits successfully, account created with invalid email | Error message "Please enter a valid email address" should appear | Screenshot_01.png
BUG-002 | TC_UAM_010 | User Account | Login with empty fields submits without validation | User can click Login button with both email and password fields empty - page refreshes with no error message | High | P2 | In Progress | 2026-03-01 | Amisha Modi | Dev Team | Safari v17 | 1. Go to Login page 2. Leave both email and password fields empty 3. Click Login button | Page refreshes, no error message displayed, fields remain empty | Validation error messages should appear for required fields | Screen Recording_01.mp4
BUG-003 | TC_UAM_018 | User Account | Email changed without verification | User can change email address without any verification - security risk | High | P2 | Open | 2026-03-02 | Amisha Modi | Dev Team | Chrome v122 | 1. Login to account 2. Go to Account Information 3. Change email to new address | Email updates immediately, no verification email sent | Verification email should be sent to new address, account should remain pending until verified | Screenshot_02.png
BUG-004 | TC_UAM_024 | User Account | Facebook login integration broken | Clicking "Login with Facebook" returns 404 error page | Medium | P3 | Open | 2026-03-03 | Amisha Modi | Dev Team | Chrome v122 | 1. Go to Login page 2. Click "Login with Facebook" button | 404 error page displayed | Redirect to Facebook login page | Screenshot_03.png
BUG-005 | TC_CAT_003 | Product & Catalog | Sub-category navigation shows empty page | Clicking on "Mobile Phones" sub-category under Electronics displays empty page with no products | High | P2 | Open | 2026-03-02 | Amisha Modi | Dev Team | Chrome v122 | 1. Go to homepage 2. Hover over Electronics 3. Click "Mobile Phones" sub-category | Empty page with message "There are no products to list in this category" | Mobile phones products should be displayed | Screenshot_04.png
BUG-006 | TC_CAT_010 | Product & Catalog | Empty search shows "no results" instead of all products | When user clicks Search with empty field, it shows "Your search returned no results" instead of displaying all products | Medium | P3 | Open | 2026-03-02 | Amisha Modi | Dev Team | Chrome v122 | 1. Go to Search 2. Leave search field empty 3. Click Search button | "Your search returned no results" message displayed | All products should be displayed or prompt to enter search term | Screenshot_05.png
BUG-007 | TC_CAT_023 | Product & Catalog | Filter persistence lost after page reload | When user applies filters and reloads page, all filters are reset | Medium | P3 | Open | 2026-03-03 | Amisha Modi | Dev Team | Chrome v122 | 1. Go to Category page 2. Apply price filter ($500-$1000) 3. Reload page | Filters reset to default | Filters should persist in URL or session | Screenshot_06.png
BUG-008 | TC_CAT_029-034 | Product & Catalog | Product comparison feature completely broken | Product comparison feature returns 404 error or is completely missing | High | P2 | Open | 2026-03-03 | Amisha Modi | Dev Team | Chrome v122 | 1. Go to any product 2. Look for "Compare" option 3. Click if available | Compare option missing OR clicking shows 404 error | Compare option should be available and functional | Screenshot_07.png
BUG-009 | TC_CART_010 | Cart | Tax calculation uses wrong rate | Tax calculation shows 8% instead of configured 10% tax rate | Critical | P1 | In Progress | 2026-03-04 | Amisha Modi | Dev Team | Chrome v122 | 1. Add product with price $100 to cart 2. Enter address with 10% tax rate 3. View cart total | Total shows $108 ($100 + $8 tax) | Total should show $110 ($100 + $10 tax) | Screenshot_08.png
BUG-010 | TC_CART_017 | Cart | Cart not syncing across browser tabs | When user adds item in one tab, other tab doesn't update automatically | Medium | P3 | Open | 2026-03-04 | Amisha Modi | Dev Team | Chrome v122 | 1. Open two tabs with site 2. In Tab A, add item to cart 3. Check Tab B cart icon | Tab B still shows old cart count | Tab B should update automatically without refresh | Screen Recording_02.mp4
BUG-011 | TC_CART_018 | Cart | Cart not syncing across devices | When user adds item on Device A, cart on Device B doesn't update | Medium | P3 | Open | 2026-03-04 | Amisha Modi | Dev Team | Chrome + Safari | 1. Login on Device A and B 2. Add item on Device A 3. Check cart on Device B | Device B cart not updated | Cart should sync across devices in real-time | Screen Recording_03.mp4
BUG-012 | TC_SEC_001 | Security | No rate limiting on login attempts | User can make unlimited failed login attempts without any lockout or CAPTCHA | Critical | P1 | Fixed | 2026-03-05 | Amisha Modi | Dev Team | Chrome v122 | 1. Go to Login page 2. Enter wrong password 20+ times 3. Continue trying | No lockout, no CAPTCHA, unlimited attempts allowed | After 5 failed attempts, account should lock or CAPTCHA should appear | Screenshot_09.png
BUG-013 | TC_SEC_002 | Security | Password reset reveals if email exists | System shows different messages for registered vs unregistered emails | High | P2 | Fixed | 2026-03-05 | Amisha Modi | Dev Team | Chrome v122 | 1. Go to Forgot Password 2. Enter unregistered email 3. Submit | Message: "Email address not found in our system" | Generic message: "If email exists, reset link will be sent" | Screenshot_10.png
BUG-014 | TC_SEC_003 | Security | Session cookie missing Secure flag | Session cookie does not have Secure flag set, potential security risk | High | P2 | In Progress | 2026-03-06 | Amisha Modi | Dev Team | Chrome v122 | 1. Login to application 2. Open Developer Tools > Application > Cookies 3. Check cookie attributes | Secure flag not set for session cookie | Secure flag should be set to true | Screenshot_11.png
KEY METRICS SUMMARY
Metric | Value
Total Bugs Found | 14
Critical Bugs | 2 (14%)
High Severity Bugs | 6 (43%)
Medium Severity Bugs | 6 (43%)
Low Severity Bugs | 0 (0%)
Fixed Bugs | 2
Open Bugs | 8
In Progress | 3
Bug Density | 5.5 bugs per 100 test cases
Modules with Most Bugs | User Account (4), Product & Catalog (4)

## Bug Summary by Module
Module | Critical | High | Medium | Low | Total
User Account | 0 | 2 | 2 | 0 | 4
Product & Catalog | 0 | 2 | 2 | 0 | 4
Cart | 1 | 0 | 2 | 0 | 3
Checkout | 0 | 0 | 0 | 0 | 0
Order | 0 | 0 | 0 | 0 | 0
Payment | 0 | 0 | 0 | 0 | 0
Tax & Shipping | 0 | 0 | 0 | 0 | 0
Inventory | 0 | 0 | 0 | 0 | 0
Admin | 0 | 0 | 0 | 0 | 0
Admin Role | 0 | 0 | 0 | 0 | 0
Reports | 0 | 0 | 0 | 0 | 0
Notifications | 0 | 0 | 0 | 0 | 0
Promotions | 0 | 0 | 0 | 0 | 0
Security | 1 | 2 | 0 | 0 | 3
TOTAL | 2 | 6 | 6 | 0 | 14

## Bug Severity Breakdown
Severity | Count | Percentage | Description
Critical | 2 | 14% | System crash, data loss, security breach, major feature broken
High | 6 | 43% | Major feature not working, no workaround, security risk
Medium | 6 | 43% | Feature works with issues, workaround available
Low | 0 | 0% | Cosmetic issues, minor UI glitches

## Bug Priority Breakdown
Priority | Count | Percentage | Action Timeline
P1 - Urgent | 2 | 14% | Must be fixed immediately (within 24 hours)
P2 - High | 6 | 43% | Should be fixed before next release (this sprint)
P3 - Medium | 6 | 43% | Can be fixed in next release cycle
P4 - Low | 0 | 0% | Fix when time permits (backlog)

## Bug Status BreakdownStatus
Status | Count | Percentage
Open | 8 | 57%
In Progress | 3 | 21%
Fixed | 2 | 14%
Closed | 1 | 7%
Deferred | 0 | 0%
Cannot Reproduce | 0 | 0%

## Bug Lifecycle
Defect Lifecycle Flow for OpenCart Project:
┌──────────┐
│ NEW │
└────┬─────┘
│
▼
┌──────────┐
│ ASSIGNED │
└────┬─────┘
│
┌──────────┼──────────┐
▼ ▼ ▼
┌──────────┐┌──────────┐┌──────────┐
│ FIXED ││ REJECTED ││INVALID │
└────┬─────┘└────┬─────┘└────┬─────┘
│ │ │
▼ │ │
┌──────────┐ │ │
│ VERIFIED │ └─────┬─────┘
└────┬─────┐ │
│ │ │
▼ │ │
┌──────────┐│ │
│ CLOSED │◀───────────┘
└──────────┘
▲
│
┌────┴─────┐
│ REOPEN │
└──────────┘
Current Status:
• NEW : 0 bugs
• ASSIGNED : 8 bugs
• FIXED : 2 bugs
• VERIFIED : 1 bug
• CLOSED : 1 bug
• REJECTED : 0 bugs
• REOPEN : 0 bugs
• INVALID : 0 bugs